## Objective 1
Overarching Goal: Reduce people's risk for chronic disease and the upward trend of overweight and obesity through strategies focusing on physical activity, nutrition and healthy weight.
Goal: Take an inventory of current resources across the region that address physical activity, nutrition and healthy weight; compare those resources against evidence-based practices and define areas in need of improvement.
Objective 1: Conduct presentations in each county, present the findings of the PHIP process and gather feedback regarding community resources that relate to physical activity, nutrition and healthy weight.
| 2014 | 2015 | 2016 | 2017 | 2018 | NCHD Team & Community Partners
Action Step 1.1 Host a meeting in each of our six counties by the end of 2013, inviting community members and stakeholders, to present the PHIP plan. | Meetings held communities in all six counties Status: Completed in 2014; Ongoing | Include PHIP in community presentations and meeting Status: Completed in 2015; Ongoing | Include PHIP in community presentations and meeting Status: Completed in 2016; Ongoing | Include PHIP in community presentations and meeting Status: Ongoing | Include PHIP in community presentations and meeting | Tony Cappello, Deanna Herbert, Penny Stumpf, Sherri Yahn, Trish McClain, Michelle Pemberton, Kandice Kramer, other staff
Action Step 1.2 Gather an inventory of current community/county resources from key informants, stakeholders and community members that address the overarching goal, by the end of June, 2014. | NCHD created an inventory of healthy food, physical activity and nutrition available in each county Status: Initial inventory for all 6 counties created in 2014. | Pregnancy Related Depression resource list developed Status: Updated 2014 inventory and created Mental Health Inventory | Inventory of healthy food, physical activity and nutrition available in Yuma County updated and more complete (Vista at RCRC) Status: Update 2015 inventory | Status: Ongoing |  | Deanna Herbert, Michelle Pemberton, Sherri Yahn, Rural Communities, Resource Center (RCRC),

## Objective 2
Overarching Goal: Reduce people's risk for chronic disease and the upward trend of overweight and obesity through strategies focusing on physical activity, nutrition and healthy weight.
Goal: Evaluate how mental health and oral health contribute, influence and impact our overarching goal.
Objective 2: Identify and evaluate the oral health and mental health connections to the overarching goal.
| 2014 | 2015 | 2016 | 2017 | 2018 | NCHD Team & Community Partners
Action Step 2.1 Initiate a partnership with Centennial Mental Health, and other mental health providers/agencies, to promote and investigate the interactions between mental health and our overarching goal. | Pregnancy Related Depression focus of Maternal Child Health; Partner with Assuring Better Child Health Development (ABCD); Partner with private therapists; Healthy Steps Home Visitation initated Status: Partnerships with mental health providers initiated | Pregnancy Related Depression focus of Maternal Child Health; Healthy Steps home visitation Status: Strengthened mental health partnerships in 2015 | Partnered with Baby Bear Hugs (BBH) on LAUNCH planning and wrote implementation grant to focus on early childhood mental health; Healthy Steps home visitation; State Innovation Model initated Status: Strengthened mental health partnerships in 2016 | State Innovative Model implemented; Communities that Care initiated; additional exploration into early childhood mental health; Healthy Steps home visitation Status: Ongoing and maintaining mental health partnerships |  | Michelle Pemberton, Sherri Yahn, Amy Nation, Kandice Kramer, Alison Volgamore, Jennifer Kerr, Mraia Foy, Trish McClain, Assuring Better Child Health Development (ABCD), Maternal, Infant and Early Childhood Home Visiting (MIECHV), Maternal Child Health, Colorado Department of Public Health & Environment (CDPHE), Baby Bear Hugs, Centennial Mental Health Center (CMHC), Private therapists, Morgan County Family Center, Early Childhood Council of Logan, Phillips, Sedgwick Counties (ECCLPS), Morgan County Early Childhood Council (MCECC), Early Childhood Council of Yuma, Washington, Kit Carson Counties (ECCYWKC), RE-1 Valley Schools, Otis Schools, Yuma Schools, Rural Communities Resource Center (RCRC), NE BOCES,
Action Step 2.2 Utilize newly-hired dental hygienist to assist with identifying the gaps in the oral health system that could affect the overarching goal. | Oral health assessment, Smiles Across the Plains Strategic Plan developed; School-based oral health program expanded to include Logan and Morgan Counties Status: Completed in 2014 | Applied for Virtual Dental Home (VDH) planning grant through Caring for Colorado Foundation; School-based oral health program in all schools in all six counties Status: Completed in 2015 | VDH Planning grant; oral health business plan; School-based oral health program in all schools in all six counties Status: Completed in 2016 | VDH Planning with Salud Family Health Centers for implementation; School-based oral health program in all six counties; implement oral health business plan Status: Ongoing |  | Michelle Pemberton, Alisa Dykstra (RDH), Kandice, Kramer, Peggy McLinn, Tina Kohl, Penny Stumpf, Rachael Motzkus (RDH), Rural Communities Resource Center (RCRC), Sally Henry (Consultant), Kit Carson Public Health, Lincoln County Public Health, Salud Family Health Center, Cheyenne County Public Health, Patty Armbruster (RDH), Centennial Area Health Education Center (CAHEC), other private dentists and dental hygienists,
Action Step 2.3 Evaluate the effectiveness of the partnerships with oral and mental health partners to determine the need for continued or innovative interventions, through June, 2018. | Status: Not Completed | Status: Not Completed | Status: Not Completed | Status: In process

## Objective 3
Overarching Goal: Reduce people's risk for chronic disease and the upward trend of overweight and obesity through strategies focusing on physical activity, nutrition and healthy weight.
Goal: Increase awareness of the overwieight/obesity and chronic disease issues in the northeast region.
Objective 3: Develop an advertising and social marketing campaign to increase the awareness of our overarching goal.
| 2014 | 2015 | 2016 | 2017 | 2018 | NCHD Team & Community Partners
Action 3.1 Utilize NCHD resources and social media to help support and encourage local efforts that address the overarching goal. | Developed and implemented "I Am Healthy NE" campaign; Focus of Health Fair boards we took to all communities in six counties; Status: Initiated media campaign in 2014 | Continue "I Am Healthy NE" campaign; Focus of Health Fair boards we took to all communities in six counties; Status: Maintained media campaign initiated in 2015 | Continue "I Am Healthy NE" campaign, Developed and implemented Week of the Young Child campaign; Focus of Health Fair boards we took to all communities in six counties; Status: Expanded partnerships with local efforts and media campaign | Continue "I Am Healthy NE" campaign; Continue Week of the Young Child campaign, Developed Radon awareness campaign; Assisted with development of Health Fest; Focus of Health Fair boards we took to all communities in six counties. Status: Further expansion of partnerships woth local efforts and media campaign |  | Deanna Herbert, Penny Stumpf, Jessa Hatch, Tammy Hort, Mel Bustos, Amber Donovan, Ann Clouse, Heather Coin, Teena Pierce, Bill Helms, Sherri Yahn, Michelle Pemberton, miscellaneous staff working Health Fair booths, City of Sterling, Rural Communities Resource Center (RCRC),
Action 3.2 Evaluate the effectiveness of social marketing/educational campaigns and strategies to determine the need for continued or innovative interventions, through June, 2018. | Status: Not Completed | Status: Informal evaluation of effectiveness of marketing campaigns to plan next steps; Transition in the Public Information Officer position | Status: Informal evaluation of effectiveness of marketing campaigns to plan next steps; New Public Information Officer Hired | Status: Informal evaluation of effectiveness of marketing campaigns to plan next steps

## Objective 4
Overarching Goal: Reduce people's risk for chronic disease and the upward trend of overweight and obesity through strategies focusing on physical activity, nutrition and healthy weight.
Goal: Partner with and/or support existing and new concepts/programs/resources that support the emphasis area of physical activity, nutrition and healthy weight.
Overarching Goal: Reduce people's risk for chronic disease and the upward trend of overweight and obesity through strategies focusing on physical activity, nutrition and healthy weight.
Goal: Partner with and/or support existing and new concepts/programs/resources that support the emphasis area of physical activity, nutrition and healthy weight.
Objective 4: Identify funding opportunities to address the overarching goal.
| 2014 | 2015 | 2016 | 2017 | 2018 | NCHD Team & Community Partners
Action Step 4.1 Seek grant funding that will address the issues of physical activity, nutrition and healthy weight. | Office of Planing & Partnership mini-grant; Grants for school-based oral health program; Tobacco program Status: Completed in 2014 | Office of Planing & Partnership mini-grant; Grants for school-based oral health program and initiation of elder oral health program; applied for funding for Tobacco Grants Program and Cancer, Cardiovascular and Chronic Pulmonary Disease Grants Program (CCPD); Status: Completed in 2015 | Office of Planing & Partnership mini-grant; Continued grants and implementation of school-based oral health program and elder oral health program; Implementation of Tobacco and CCPD programs; Applied and implemented a Virtual Dental Home (VDH) planning grant; Applied for LAUNCH grant (early childhood mental health); Applied for and implemented State Innovation Model (SIM); Applied and implemented Radon Awareness grant program Status: Completed in 2016 | Office of Planing & Partnership mini-grant; Continued grants and implementation of school-based oral health program and elder oral health program; Implementation of Tobacco and CCPD programs; Continued SIM; Continued Radon awareness program; Just Check It Program implemented; Applied and implemented Communities that Care project Status: Ongoing |  | Deanna Herbert, Jessa Hatch, Michelle Pemberton, Alisa Dykstra (RDH), Kandice Kramer, Peggy McLinn, Rachael Motzkus (RDH), Tina Kohl, Penny Stumpf, Jenna Florian, Kareen Cox, Ann Clouse, Kathy Anderson, Lynn Bournia, Shanna Wisdom, Rosemary Lengel, Mickie George, Christine Covelli, Jessica Lundgren, Sandra Guiterrez, Taylor Guzman, Janet Vazquez-Yanez, Jodi Murray, Bereniece Contreras, Kate Barnes, Maria Melendez, Sherri Yahn, Rural Communities Resource Center (RCRC), Baby Bear Hugs (BBH), Assuring Better Child Health Development (ABCD), Centennial Mental Health Center (CMHC), RE-1 Valley Schools, Otis Schools, Yuma Schools, Idalia Schools, Wray Schools, Akron Schools, Brush Schools, Wiggins Schools, Weldon Valley Schools, Fleming Schools, Holyoke Schools, Julesburg Schools, Peetz Schools
Action Step 4.2 Utilize newly-hired dental hygienist to assist with the gaps in the oral health system that could affect the overarching goal. | Oral Health Assessment; Expanded school-based oral health program to Logan and Morgan Counties Status: Completed in 2014 | Continued school-based oral health program in all six counties; expanded to include elder oral health program Status: Completed in 2015 | Applied and implemented a Virtual Dental Home (VDH) planning grant; Dental Hygeinist begins working in our Tobacco program; Developed oral health business plan for oral health program; continued school-based and elder oral health programming Status: Completed in 2016 | Oral Health Assessment; continued school-based and elder oral health programming; continued planning with Salud Family Health Center for implementation of VDH; continued integraion of oral and tobacco programs, Status: Ongoing |  | Michelle Pemberton, Alisa Dykstra (RDH), Kandice Kramer, Rachael Motzkus (RDH), Penny Stumpf, Tina Kohl, Peggy McLinn, Patti Armbruster (RDH), Salud Family Health Center, Rural Communities Resource Center (RCRC), Schools
Action Step 4.3 Utlize the resources available through local mental health providers to identify the gaps in the mental health system that could affect the overarching goal. | Pregnancy Related Depression focus of Maternal Child Health; Partner with Assuring Better Child Health Development (ABCD); Partner with private therapists; Healthy Steps Home Visitation initated Status: Initiated in 2014 | Pregnancy Related Depression focus of Maternal Child Health; Healthy Steps home visitation Status: Completed in 2015 | Partnered with Baby Bear Hugs (BBH) on LAUNCH planning and wrote implementation grant to focus on early childhood mental health; Healthy Steps home visitation Status: Completed in 2016 | State Innovative Model initiated; Communities that Care initiated; additional exploration into early childhood mental health; Healthy Steps home visitation Status: Ongoing |  | Michelle Pemberton, Sherri Yahn, Amy Nation, Kandice Kramer, Alison Volgamore, Jennifer Kerr, Mraia Foy, Trish McClain, Assuring Better Child Health Development (ABCD), Maternal, Infant and Early Childhood Home Visiting (MIECHV), Maternal Child Health, Colorado Department of Public Health & Environment (CDPHE), Baby Bear Hugs, Centennial Mental Health Center (CMHC), Private therapists, Morgan County Family Center, Early Childhood Council of Logan, Phillips, Sedgwick Counties (ECCLPS), Morgan County Early Childhood Council (MCECC), Early Childhood Council of Yuma, Washington, Kit Carson Counties (ECCYWKC), RE-1 Valley Schools, Otis Schools, Yuma Schools, Rural Communities Resource Center (RCRC), NE BOCES,

## Objective 5
Overarching Goal: Reduce people's risk for chronic disease and the upward trend of overweight and obesity through strategies focusing on physical activity, nutrition and healthy weight.
Goal: Partner with and/or support existing and new concepts/programs/resources that support the emphasis area of physical activity, nutrition and healthy weight.
Objective 5: Promote school and early learning center policies and programs that increase physical activity, nutrition and healthy weight.
| 2014 | 2015 | 2016 | 2017 | 2018 | NCHD Team & Community Partners
Action Step 5.1 Partner with CSU with a grant through May, 2016 to decrease obesity in northeast Colorado and increase heart health education with elementary students. | Status: Did not get this grant |  |  |  |  | Tony Cappello, Trish McClain, Colorado State University (CSU)
Action Step 5.2 Identify an inventory of evidence-based practices aimed at schools that address the overarching goal, for the 2014-2015 school year. | Office of Planning & Partnerships at the Colorado Department of Public Health & Environment (CDPHE) website offers a list of evidence-based practices; Status: Initiated in 2014 | CCPD Grant Program offers evidence-based practices Status: Completed in 2015 |  |  |  | Deanna Herbert, Penny Stumpf, Michelle Pemberton, Colorado Department of Public Health & Environment (CDPHE)
Action Step 5.3 Evaluate the effectiveness of school and early learning center programs to determine the need for continued or innovative interventions, through June, 2018. | Status: Not Completed in 2014 | Status: Not Completed in 2015 | Developed a CCPD Evaluation Plan Status: Initiated in 2016 | Implementation of CCPD Evaluation Plan Status: Ongoing |  | Penny Stumpf, Kareen Cox, Jenna Florian, Ann Clouse, Kathy Anderson, Colorado Department of Public Health & Environment (CDPHE), Kaiser Permanente,