## Sheet1
| 2011-10-11 | 2011-11-11 | 2011-12-11 | 2012-01-11 | 2012-02-11 | 2012-03-11 | 2012-04-11 | 2012-05-11 | 2012-06-11 | 2012-07-11 | 2012-08-11 | 2012-09-11 | 2012-10-11 | 2012-11-11 | 2012-12-11
Organize for Success / Partnership Development | bar: 2011-10-11 to 2011-12-11
Determine why the MAPP process is needed | bar: 2011-10-11
Identify, organize, and recruit participants | bar: 2011-10-11 to 2011-11-11
Design the planning process | bar: 2011-11-11 to 2011-12-11
Assess resource needs | bar: 2011-11-11
Conduct a readiness assessment | bar: 2011-11-11
Develop a workplan, timeline, and other tools | bar: 2011-11-11 to 2011-12-11
Visioning | bar: 2011-11-11 to 2012-01-11
Prepare for and design the visioning process | bar: 2011-11-11 to 2011-12-11
Hold visioning sessions | bar: 2012-01-11
Celebrate successes and achievements to date | bar: 2012-01-11
4 MAPP Assessments | bar: 2012-02-11 to 2012-06-11
Community Themes and Strengths Assessment | bar: 2012-02-11 to 2012-06-11
Identify subcommittee, approaches, and resources | bar: 2012-02-11 to 2012-03-11
Hold community dialogues and focus groups | bar: 2012-03-11 to 2012-07-11
Compile results/identify challenges and opportunities | bar: 2012-05-11 to 2012-06-11
Local Public Health System Assessment | bar: 2012-03-11 to 2012-05-11
Prepare for the LPHSA/ establish subcommittee | bar: 2012-03-11 to 2012-04-11
Discuss the Essential Services/identify org. activities | bar: 2012-04-11
Respond to the performance measures instrument | bar: 2012-04-11 to 2012-05-11
Discuss results/identify challenges and opportunities | bar: 2012-05-11
Community Health Status Assessment | bar: 2012-05-11 to 2012-06-11
Conduct data collection of core indicators | bar: 2012-05-11
Select and collect additional indicators | bar: 2012-05-11
Analyze the data / create a health profile | bar: 2012-05-11
Disseminate health profile | bar: 2012-05-11 to 2012-06-11
Establish a system to monitor data over time | bar: 2012-05-11 to 2012-06-11
Identify CHSA challenges and opportunities | bar: 2012-06-11
Forces of Change Assessment | bar: 2012-05-11 to 2012-06-11
Prepare for the Forces of Change Assessment | bar: 2012-05-11
Hold brainstorming session with committee | bar: 2012-05-11
Simplify list / identify threats and opportunities | bar: 2012-06-11
Identify Strategic Issues | bar: 2012-07-11 to 2012-09-11
Celebrate successes and completion of assessments | bar: 2012-07-11
Identify potential strategic issues | bar: 2012-07-11 to 2012-08-11
Discuss issues-why they are strategic and urgency | bar: 2012-08-11
Consolidate strategic issues | bar: 2012-09-11
Arrange issues in priority order | bar: 2012-09-11
Formulate Goals and Strategies | bar: 2012-09-11 to 2012-11-11
Develop goal statements | bar: 2012-09-11 to 2012-10-11
Develop strategy alternatives and barriers | bar: 2012-09-11 to 2012-10-11
Explore implementation details | bar: 2012-09-11 to 2012-10-11
Select and adopt strategies | bar: 2012-10-11 to 2012-11-11
Draft the planning report | bar: 2012-10-11 to 2012-11-11
Celebrate successes and recognize achievements | bar: 2012-10-11
The Action Cycle* | bar: 2012-11-11 to 2012-12-11
Organize for action | bar: 2012-11-11
Develop objectives and agree on accountability | bar: 2012-11-11
Develop action plans | bar: 2012-11-11
Coordinate action plans and implement | bar: 2012-12-11
Prepare for evaluation / determine the methodology | bar: 2012-11-11
Gather evidence and justify conclusions | bar: 2012-12-11
Share results | bar: 2012-12-11