## Sheet1
North Central District Health Department |  | Existing accreditation activities have been mapped on this timeline. Additional activities will be mapped as they are identified.
Accreditation Preparation Timeline
TASK | STAFF | [5 empty] | TIMELINE
|  | 2014-01-01 | 2014-02-01 | 2014-03-01 | 2014-04-01 | 2014-05-01 | 2014-06-01 | 2014-07-01 | 2014-08-01 | 2014-09-01 | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01
Performance Management | MS | [9 empty] | ongoing
Quality Improvement | MS | [9 empty] | ongoing
PHAB online accreditation orientation | MS / RW
Activate accreditation team | MS
Hold accreditation team meetings | All
Conduct brief refresher of accreditation information | MS - Staff
Review completed prerequisites | MS / KLS / RW
Identify next time frame for CHA/CHIP process | AE / MS / RW
Review department mission and vision | MS - Staff
Identify department values | All
Review 3 core functions and 10 essential services | MS - Staff
Cover PHAB documentation guidelines | MS - All
Develop process to select potential documentation | All
Identify approach to full team review of Standards & Measures | All
Conduct full team review of Standards and Measures | All
Gather documentation / consider timeframes required | All
Complete strategic plan | AE / MS / RW
Complete Workforce Development plan | MS
Submit Letter of Intent | MS
Apply for accreditation | MS
(Assessment) DOMAIN 1 | KLS / VH
(Investigation) DOMAIN 2 | PH
(Communication) DOMAIN 3 | MS / SB
(Engage community) DOMAIN 4 | VH / KLS
(Develop policies/plans) DOMAIN 5 | AE / RW
(Enforce laws/regulations) DOMAIN 6 | PH
(Improve access to healthcare) DOMAIN 7 | VH / KLS
(Workforce Development) DOMAIN 8 | AE / MS
(Perf Mgmt / QI) DOMAIN 9 | MS
(Contribute / apply evidence base) DOMAIN 10 | PH / SB / VH
(Management and Administration) DOMAIN 11 | AE / MS / RW
(BOH) DOMAIN 12 | AE / MS / RW